## Overview Dashboard
DEXTRA MANAGEMENT CONSOLE & PROGRESS DASHBOARD
| TOTAL BACKLOG TASKS | COMPLETED TASK ITEMS | PROJECT COMPLETION PROGRESS | ACTIVE QA TICKETS | Developer | Total Days | Status | Count
| 10 | 3 | 30% | 0 | Salman | 5 | To Do | 7
[5 empty] | Logesh | 5 | In Progress | 1
[5 empty] | Muthamil | 2 | Done | 2
[5 empty] | Godfrey | 2

## Trello Board & Tasks
DEXTRA PROJECT TASK ALLOTMENT BOARD
BOARD METRICS
| Total Tasks | 10
| Completed Tasks | 3
| Progress % | 30%
Task ID | Board Column | Owner | Module | Responsibilities & Tasks | Primary Files | Completed? | Start Date | End Date | Duration (Days) | Helper Test Cases
T01 | Done | Salman | Camera Feed & Preprocessing | Initialize camera index capture stream using OpenCV; crop, mirror, and scale frames matching MediaPipe requirements. | python/camera.py | TRUE | 2026-06-26 | 2026-06-27 | 1 | Confirm VideoCapture opens device and releases locks cleanly.
T02 | To Do | Salman | MediaPipe Landmark Tracker | Run MediaPipe Hands model; detect and extract normalized coordinate array points for 21 landmarks. | python/gesture_engine.py | FALSE | 2026-06-28 | 2026-06-30 | 2 | Verify tracking execution loop runs locally and outputs [0.0, 1.0] float coords.
T03 | To Do | Salman | Mouse Execution Mapper | Apply NumPy coordinate interpolation and moving average filter; execute clicks, scrolls, and drags via PyAutoGUI. | python/gesture_mapping.py | FALSE | 2026-06-28 | 2026-06-30 | 2 | Test boundary coords (0 to screen width/height); verify cooldown prevents duplicate clicks; verify open palm freeze.
T04 | To Do | Logesh | Wakeword Detector | Record background sound blocks using sounddevice; scan audio blocks for 'DEXTRA' custom activation keyword. | python/voice_wakeword.py | FALSE | 2026-07-01 | 2026-07-03 | 2 | Verify microphone initialization and background ambient noise calibration.
T05 | To Do | Logesh | Hugging Face Transcriber | Load Hugging Face transformers pipeline (Whisper-tiny); decode audio stream buffers into text commands. | python/voice_engine.py | FALSE | 2026-07-01 | 2026-07-03 | 2 | Verify model imports and downloads locally; verify audio file segment STT translates in <500ms.
T06 | To Do | Logesh | Voice Command Mapper | Map transcribed text keywords to PyAutoGUI key hotkeys (e.g. 'copy' triggers Ctrl+C). | python/voice_mapping.py | FALSE | 2026-07-04 | 2026-07-05 | 1 | Verify spoken navigation string matches mapped key command; test error logs for invalid words.
T07 | To Do | Muthamil | Config Database Manager | Thread-safe read and write operations persisting parameters to settings.json and custom_gestures.json. | python/config.py | FALSE | 2026-06-26 | 2026-06-27 | 1 | Confirm configuration values fall within target boundaries; test concurrent writes locks.
T08 | To Do | Muthamil | FastAPI Backend GUI Server | Serve settings endpoints; host WebSocket feed streaming annotated JPEG frames; launch interactive menu CLI. | python/gui_server.py, python/main.py | FALSE | 2026-07-04 | 2026-07-05 | 1 | Verify FastAPI initializes port 8000; verify GET/POST endpoints; test WebSocket connection disconnect recovery.
T09 | Done | Godfrey | React Settings GUI Console | Build dark themed sliders/toggles to configure thresholds, camera indices, and custom wakewords. | Frontend/ | TRUE | 2026-06-26 | 2026-06-27 | 1 | Verify Vite local dev server runs on port 5173; verify forms state bindings to FastAPI REST schema.
T10 | In Progress | Godfrey | Gesture Trainer Console | Develop HTML5 Canvas canvas drawing annotated WebSocket image streams; capture coordinates for custom gestures. | Frontend/ | TRUE | 2026-07-06 | 2026-07-07 | 1 | Verify Canvas renders streams smoothly at 30 FPS; verify save forms upload JSON structure.

## Developer Worklogs
DEXTRA DAILY WORKLOGS - LIVE UPDATES
Log ID | Date | Developer | Task ID Reference | Daily Work Details / Progress | Hours Logged | Status Update
L01 | 2026-06-26 |  | T01
L02 | 2026-06-27 | Godfrey | T09 | Completed the gui light themed sliders/toggles to configure thresholds, camera indices, and custom wakewords. | 3hrs | Done

## Bug Tracker & QA Logs
DEXTRA QA BUG TRACKER & TICKETS
Bug ID | Target Module | Severity | Bug Description | Assigned Owner | Status | Date Opened | Date Closed | Resolution Notes
B01 |  | Medium |  |  | Closed | 2026-06-28 | 2026-06-28