## Overview Dashboard
DEXTRA MANAGEMENT CONSOLE & PROGRESS DASHBOARD
| TOTAL BACKLOG TASKS | COMPLETED TASK ITEMS | PROJECT COMPLETION PROGRESS | ACTIVE QA TICKETS | Developer | Total Days | Status | Count
[5 empty] | Salman |  | To Do
[5 empty] | Logesh |  | In Progress
[5 empty] | Muthamil |  | Done
Godfrey
Done

## Trello Board & Tasks
DEXTRA PROJECT TASK ALLOTMENT BOARD
BOARD METRICS
Total Tasks
Completed Tasks
Progress %
Task ID | Board Column | Owner | Module | Responsibilities & Tasks | Primary Files | Completed? | Start Date | End Date | Duration (Days) | Helper Test Cases
T00 | Done | Harihar R | System Ideation & Concept | Conceived initial gesture-driven control concept, system requirements, and core architectural vision. | README.md, DEXTRA_Proposal.pptx | TRUE | 2026-06-20 | 2026-06-25
T01 | Done | Mohamed Salman P | Camera Feed & Preprocessing | Initialize camera index capture stream using OpenCV; crop, mirror, and scale frames matching MediaPipe requirements. | python/camera.py | TRUE | 2026-06-26 | 2026-06-27 |  | Confirm VideoCapture opens device and releases locks cleanly.
T02 | Done | Mohamed Salman P | MediaPipe Landmark Tracker | Run MediaPipe Hands model; detect and extract normalized coordinate array points for 21 landmarks. | python/gesture_engine.py | TRUE | 2026-06-28 | 2026-06-30 |  | Verify tracking execution loop runs locally and outputs [0.0, 1.0] float coords.
T03 | Done | Mohamed Salman P | Mouse Execution Mapper | Apply NumPy coordinate interpolation and moving average filter; execute clicks, scrolls, and drags via PyAutoGUI. | python/gesture_mapping.py | TRUE | 2026-06-28 | 2026-06-30 |  | Test boundary coords (0 to screen width/height); verify cooldown prevents duplicate clicks; verify open palm freeze.
T04 | Done | Logesh M | Wakeword Detector | Record background sound blocks using sounddevice; scan audio blocks for 'DEXTRA' custom activation keyword. | python/voice_wakeword.py | TRUE | 2026-07-01 | 2026-07-03 |  | Verify microphone initialization and background ambient noise calibration.
T05 | Done | Logesh M | Hugging Face Transcriber | Load Hugging Face transformers pipeline (Whisper-tiny); decode audio stream buffers into text commands. | python/voice_engine.py | TRUE | 2026-07-01 | 2026-07-03 |  | Verify model imports and downloads locally; verify audio file segment STT translates in <500ms.
T06 | Done | Logesh M | Voice Command Mapper | Map transcribed text keywords to PyAutoGUI key hotkeys (e.g. 'copy' triggers Ctrl+C). | python/voice_mapping.py | TRUE | 2026-07-04 | 2026-07-05 |  | Verify spoken navigation string matches mapped key command; test error logs for invalid words.
T07 | Done | Muthamil V | Config Database Manager | Thread-safe read and write operations persisting parameters to settings.json and custom_gestures.json. | python/config.py | TRUE | 2026-06-26 | 2026-06-27 |  | Confirm configuration values fall within target boundaries; test concurrent writes locks.
T08 | Done | Muthamil V | FastAPI Backend GUI Server | Serve settings endpoints; host WebSocket feed streaming annotated JPEG frames; launch interactive menu CLI. | python/gui_server.py, python/main.py | TRUE | 2026-07-04 | 2026-07-05 |  | Verify FastAPI initializes port 8000; verify GET/POST endpoints; test WebSocket connection disconnect recovery.
T09 | Done | Godfrey T R | React Settings GUI Console | Build dark themed sliders/toggles to configure thresholds, camera indices, and custom wakewords. | Frontend/ | TRUE | 2026-06-26 | 2026-06-27 |  | Verify Vite local dev server runs on port 5173; verify forms state bindings to FastAPI REST schema.
T10 | Done | Godfrey T R | Gesture Trainer Console | Develop HTML5 Canvas canvas drawing annotated WebSocket image streams; capture coordinates for custom gestures. | Frontend/ | TRUE | 2026-07-06 | 2026-07-07 |  | Verify Canvas renders streams smoothly at 30 FPS; verify save forms upload JSON structure.

## Developer Worklogs
DEXTRA DAILY WORKLOGS - LIVE UPDATES
Log ID | Date | Developer | Task ID Reference | Daily Work Details / Progress | Hours Logged | Status Update
L00 | 2026-06-25 | Harihar R | T00 | Conceived DEXTRA system architecture, touchless gesture control paradigm, and project scope. | 8hrs | Done
L01 | 2026-06-26 | Mohamed Salman P | T01 | Initialized camera capture stream using OpenCV; implemented frame cropping, mirroring, and scaling. | 4hrs | Done
L02 | 2026-06-26 | Muthamil V | T07 | Built thread-safe Config Manager persisting settings and custom gestures to JSON storage. | 3hrs | Done
L03 | 2026-06-27 | Godfrey T R | T09 | Built React Settings GUI console with real-time controls for thresholds, camera indices, and wakewords. | 4hrs | Done
L04 | 2026-06-28 | Mohamed Salman P | T02 | Implemented MediaPipe Hands model landmark tracker extracting 21 3D normalized coordinates. | 5hrs | Done
L05 | 2026-06-29 | Mohamed Salman P | T03 | Created mouse execution mapper with NumPy coordinate smoothing and PyAutoGUI click/scroll actions. | 5hrs | Done
L06 | 2026-07-01 | Logesh M | T04 | Configured sounddevice background sound recording and ambient noise calibrated wakeword engine. | 4hrs | Done
L07 | 2026-07-02 | Logesh M | T05 | Integrated Hugging Face Whisper-tiny transformer pipeline STT speech-to-text decoder. | 6hrs | Done
L08 | 2026-07-03 | Godfrey T R | T09 | Refined UI dark-themed design system, slider components, and REST API state bindings. | 3hrs | Done
L09 | 2026-07-04 | Godfrey T R | T10 | Developed Gesture Trainer UI canvas with live WebSocket streaming & custom gesture coordinate capture. | 4hrs | Done
L10 | 2026-07-04 | Logesh M | T06 | Mapped transcribed voice command keywords to PyAutoGUI OS hotkeys. | 4hrs | Done
L11 | 2026-07-05 | Muthamil V | T08 | Built FastAPI REST backend & WebSocket endpoints streaming annotated JPEG frames and trainer data. | 6hrs | Done
L12 | 2026-07-23 | Godfrey T R | T08/B02 | Diagnosed and fixed WebSocket stream disconnect handling on /trainer/stream & /voice/stream endpoints. | 4hrs | Done
L13 | 2026-07-23 | Mohamed Salman P | T02/B03 | Resolved MediaPipe clearcut telemetry upload connection errors (Status_ConnectFailed: 12029). | 3hrs | Done

## Bug Tracker & QA Logs
DEXTRA QA BUG TRACKER & TICKETS
Bug ID | Target Module | Severity | Bug Description | Assigned Owner | Status | Date Opened | Date Closed | Resolution Notes
B01 | python/camera.py | Medium | OpenCV VideoCapture camera resource locking on server restart causing frame capture freeze. | Mohamed Salman P | Closed | 2026-06-28 | 2026-06-28 | Added try-finally cleanup blocks and explicit camera.release() calls on stream shutdown.
B02 | python/gui_server.py | High | FastAPI WebSocket stream disconnect error on /trainer/stream when client closes connection. | Muthamil V | Closed | 2026-07-22 | 2026-07-23 | Handled WebSocketDisconnect exception gracefully and added client connection manager to prevent crashing worker tasks.
B03 | python/gesture_engine.py | Medium | MediaPipe clearcut telemetry upload failures (Status_ConnectFailed: 12029) due to restricted network. | Mohamed Salman P | Closed | 2026-07-22 | 2026-07-23 | Disabled Clearcut telemetry background uploads via environment configuration and suppressed offline warnings.
B04 | python/gesture_mapping.py | High | Mouse cursor jitter and accidental double-clicks during fast hand movements. | Mohamed Salman P | Closed | 2026-07-02 | 2026-07-03 | Implemented Exponential Moving Average (EMA) smoothing filter (alpha=0.35) and added click cooldown timer.
B05 | python/voice_wakeword.py | Medium | High CPU utilization and audio buffer overflow during continuous background sound recording. | Logesh M | Closed | 2026-07-03 | 2026-07-04 | Optimized sounddevice blocksize to 1024 samples and implemented ring buffer queue processing.
B06 | Git Repository | Low | Default tracking branch misalignment and orphan remote tracking branch theoriongd on GitHub. | Godfrey T R | Closed | 2026-07-23 | 2026-07-23 | Updated local remote HEAD to dextra branch and deleted obsolete theoriongd branch remotely.